## tbabers@ucsd.edu
Followup name | Group Project
User name | Triston Babers
Date | What is your current task? | What progress you have done so far? | What future plan do you have for the task? | On Holiday
Oct 11, 2022
Oct 12, 2022
Oct 13, 2022
Oct 14, 2022
Oct 15, 2022
Oct 16, 2022
Oct 17, 2022
Oct 18, 2022
Oct 19, 2022
Oct 20, 2022
Oct 21, 2022 | Meeting with Allison 10 AM today | Setup Brainstorming meeting time | Meeting on Sunday 7:30 PM over Zoom and brainstorming ideas
Oct 22, 2022
Oct 23, 2022
Oct 24, 2022 | Thinking of the Project Pitch | Added brainstorming screenshots to the GitHub Repo | Plan out how to address the Project Pitch in our next team Meeting on Thursday
Oct 25, 2022 | Adding an ADR folder to the gitHub REPO | I've copied an example ADR from the link posted on the canvas assignment | I plan to incorporate these ADR records into our team's decision making process, so we can avoid organizational debt.
Oct 26, 2022 | Adding an ADR folder to the gitHub REPO | I've copied an example ADR from the link posted on the canvas assignment | I plan to incorporate these ADR records into our team's decision making process, so we can avoid organizational debt.
Oct 27, 2022 | Working on Project Pitch | Finished slideshow | Making a C4 Diagram
Oct 28, 2022 |  |  |  | Yes
Oct 29, 2022
Oct 30, 2022
Oct 31, 2022 | Attending Project Pitch Meeting | Finished C4 Diagram for the project | Start assigning tasks to begin work on the project.
Nov 01, 2022 | Creating a GitHub Project Board | Added 13 GitHub Issues and got the board labeled with custom labels for CSS, HTML, JS, and DevOps, so we can work on tasks more efficiently. | I plan to expand it to include all of the tasks we have planned for the project so we can proceed with the project in an organized manner.
Nov 02, 2022
Nov 03, 2022 | Working on Home Page for Recipe App | Gone over logistics with group members and T.A. | Add to the current HTML of the Home page, and maybe get to the CSS if there is time.
Nov 04, 2022 | Working on home page | created HTML template | I will commit the basic home page layout: background, sample font, and maybe a top border if I have the time.
Nov 05, 2022
Nov 06, 2022
Nov 07, 2022 |  |  |  | Yes
Nov 08, 2022 |  |  |  | Yes
Nov 09, 2022 | Working on Ci/CD pipeline for GitHub | I watched a few videos, and decided to use the Super Linter for our repo. | I will finish it before the next team meeting so I can explain to everyone how it works.
Nov 10, 2022
Nov 11, 2022
Nov 12, 2022
Nov 13, 2022
Nov 14, 2022 | Creating Meeting for Monday | Posted slides | Host Meeting
Nov 15, 2022 | I'm trying to fix our linter | I have forked the main branch into a separate repo so I don't have to commit to our actual repository in order to test the github workflow | Once the linter is working correctly, I can just paste the correct workflow file into the repo directly and delete my fork.
Nov 16, 2022
Nov 17, 2022 | Attending Group Meeting | I created meeting slides to present to the group | Use the data from the meeting to determine how we should continue with the project
Nov 18, 2022 | Meeting with Home Page Team on Zoom | Scheduled the meeting for 6:00 PM on Sunday | Screen share over zoom and work on the page
Nov 19, 2022
Nov 20, 2022
Nov 21, 2022 | Going to team meeting to merge branches | Worked on home page branch and meeting notes | Talking with all the teams
Nov 22, 2022 | Recording team status video | Recorded and editted it with Meron | None, task completeted.
Nov 23, 2022
Nov 24, 2022 |  |  |  | Yes
Nov 25, 2022
Nov 26, 2022
Nov 27, 2022
Nov 28, 2022 | Prepping meeting 11/28/22 | Made meeting slides | Upload slides and notes to Github repo
Nov 29, 2022
Nov 30, 2022
Dec 01, 2022
Dec 02, 2022
Dec 03, 2022
Dec 04, 2022
Dec 05, 2022
Dec 06, 2022
Dec 07, 2022 | Working on Public Project Video | Filmed a few clips of team meetings to use in the project. | Record Project and Edit with Meron

## dcv004@ucsd.edu
Followup name | Group Project
User name | Duc Vo
Date | What is your current task? | What progress you have done so far? | What future plan do you have for the task? | On Holiday
Oct 11, 2022 | Working on 11/11/22 meeting notes and group agreement | Working with Thanh to create a draft | Finish a final draft by Thursday night to show to the team
Oct 12, 2022 | Working on 11/11/22 meeting notes and group agreement | Worked with Thanh to complete the agreement file | Finish a final draft by Thursday night to show to the team
Oct 13, 2022 |  |  |  | Yes
Oct 14, 2022 |  |  |  | Yes
Oct 15, 2022
Oct 16, 2022
Oct 17, 2022 |  |  |  | Yes
Oct 18, 2022 |  |  |  | Yes
Oct 19, 2022 |  |  |  | Yes
Oct 20, 2022 | Meeting today @5 | N/A | Send Triston meeting notes for today's meeting
Oct 21, 2022 | Brainstorm for project idea | N/A | Meet on Sunday to discuss project idea
Oct 22, 2022
Oct 23, 2022
Oct 24, 2022 |  |  |  | Yes
Oct 25, 2022 |  |  |  | Yes
Oct 26, 2022 |  |  |  | Yes
Oct 27, 2022 | Meet with team for weekly meeting | Create slides for project pitch and flow chart diagram | Finish sides and upload flow chart for project
Oct 28, 2022 | Upload flowchart by end of today | N/A | Send flowchart to Slack chat
Oct 29, 2022
Oct 30, 2022
Oct 31, 2022 | Meet with group for project pitch | N/A | N/A
Nov 01, 2022 |  |  |  | Yes
Nov 02, 2022 |  |  |  | Yes
Nov 03, 2022 | Meet with group for weekly meeting | N/A | Work on home page with Triston and Mimi
Nov 04, 2022 |  |  |  | Yes
Nov 05, 2022
Nov 06, 2022
Nov 07, 2022 | Monday meeting to discuss the progress on project | N/A | Finalize home page using html and css
Nov 08, 2022 |  |  |  | Yes
Nov 09, 2022 | Finish home page html/css for Thursday meeting | Look over some website templates for home page inspiration | Finalize home page using html and css
Nov 10, 2022 | Finish home page html/css for Thursday meeting | Code home page template | Finalize home page using html and css
Nov 11, 2022 | Finish home page html/css for Thursday meeting | Code home page template | Finalize home page using html and css
Nov 12, 2022
Nov 13, 2022
Nov 14, 2022 | Meet with team for bi-weekly meeting | N/A | Add javascript function to the home page
Nov 15, 2022 | Add JavaScript to home page | Look online to see how to implement JS to work on the home page | Incorporate add recipe page to work with home page
Nov 16, 2022 | Add JavaScript to home page | Look online to see how to implement JS to work on the home page | Incorporate add recipe page to work with home page
Nov 17, 2022 |  |  |  | Yes
Nov 18, 2022 |  |  |  | Yes
Nov 19, 2022
Nov 20, 2022
Nov 21, 2022 | Monday meeting with team | Finish up home page prototype | Add CSS to home page to finalize page
Nov 22, 2022 | Monday meeting with team | Finish up home page prototype | Add CSS to home page to finalize page
Nov 23, 2022 |  |  |  | Yes
Nov 24, 2022 |  |  |  | Yes
Nov 25, 2022 |  |  |  | Yes
Nov 26, 2022
Nov 27, 2022
Nov 28, 2022 |  |  |  | Yes
Nov 29, 2022 | Implement navbar across all three webpages | Create html for navbar | Finish navbar.html
Nov 30, 2022 | Implement navbar across all three webpages | Create html for navbar | Finish navbar.html
Dec 01, 2022 |  |  |  | Yes
Dec 02, 2022
Dec 03, 2022
Dec 04, 2022
Dec 05, 2022 | Implement navbar to be responsive and fix logo | Made navbar responsive for mobile and desktop resolutions | Finish navbar and banner resolution
Dec 06, 2022
Dec 07, 2022

## ettore.hidoux@imt-atlantique.n
Followup name | Group Project
User name | Ettore Hidoux
Date | What is your current task? | What progress you have done so far? | What future plan do you have for the task? | On Holiday
Oct 11, 2022 |  |  |  | Yes
Oct 12, 2022 |  |  |  | Yes
Oct 13, 2022 |  |  |  | Yes
Oct 14, 2022 |  |  |  | Yes
Oct 15, 2022
Oct 16, 2022
Oct 17, 2022 |  |  |  | Yes
Oct 18, 2022 |  |  |  | Yes
Oct 19, 2022 |  |  |  | Yes
Oct 20, 2022 |  |  |  | Yes
Oct 21, 2022 |  |  |  | Yes
Oct 22, 2022
Oct 23, 2022
Oct 24, 2022 |  |  |  | Yes
Oct 25, 2022 |  |  |  | Yes
Oct 26, 2022 |  |  |  | Yes
Oct 27, 2022 |  |  |  | Yes
Oct 28, 2022 |  |  |  | Yes
Oct 29, 2022
Oct 30, 2022
Oct 31, 2022 |  |  |  | Yes
Nov 01, 2022 |  |  |  | Yes
Nov 02, 2022 |  |  |  | Yes
Nov 03, 2022 | designing the source repo for the project. | starting from lab6, i did a similar structure with homogeneous name file. | write the comments, TODOs, function names to know what we have to do.
Nov 04, 2022 | starting recipe editor template html & js | js function to add recipe to recipes js function save recipes to local storage js execute when submit form | decide a data template for recipe and apply it add warning for leaving page
Nov 05, 2022
Nov 06, 2022
Nov 07, 2022 | add comments to recipe editor template html | comments made head, header and footer made add drop box area for the image | decide a data template for recipe and apply it to js function to save it to localStorage
Nov 08, 2022 |  |  |  | Yes
Nov 09, 2022 |  |  |  | Yes
Nov 10, 2022 |  |  |  | Yes
Nov 11, 2022 | update form check the output of submit | i start | css & js
Nov 12, 2022
Nov 13, 2022
Nov 14, 2022 | add function to multiply steps and add custom meal | add function to multiply steps and add custom meal | add function to multiply ingredients and tools using the work already done
Nov 15, 2022 | add tool handler | - | ingredient handler
Nov 16, 2022 | finish the javascript for editor page | create the recipe object from formData | css
Nov 17, 2022 | thinking about how integrate a utils folder or files with common functions | javascript editor page almost done | clean the javascript code
Nov 18, 2022 |  |  |  | Yes
Nov 19, 2022
Nov 20, 2022
Nov 21, 2022 | prepare the meeting | working editor page | do css
Nov 22, 2022 | shorten recipe editor js | meal type & steps | the other parts
Nov 23, 2022 |  |  |  | Yes
Nov 24, 2022 |  |  |  | Yes
Nov 25, 2022 | shortened js code | done | change image storage
Nov 26, 2022
Nov 27, 2022
Nov 28, 2022 | prepare the meeting | editor page fully working | add edition option on page
Nov 29, 2022 |  |  |  | Yes
Nov 30, 2022 | perpare meeting and add populate form handler | done | style maybe
Dec 01, 2022 | perpare meeting and add populate form handler | done | style maybe
Dec 02, 2022 |  |  |  | Yes
Dec 03, 2022
Dec 04, 2022
Dec 05, 2022 |  |  |  | Yes
Dec 06, 2022 | meeting, take notes, fix form too long because of image data | save image by itself in localstorage | implement it
Dec 07, 2022

## tnphan@ucsd.edu
Followup name | Group Project
User name | Thanh Phan
Date | What is your current task? | What progress you have done so far? | What future plan do you have for the task? | On Holiday
Oct 11, 2022 | Writing Team Working Contract and Meeting Minutes with Duc | I have finished the draft for the contract and waiting for the team to decide for any additional points and confirm the rules for all members | After the team confirmation on the rules and finalized any additional comments to the contract, I will finalize the draft and add it to the Team Repo for final review.
Oct 12, 2022 | Finalizing the Team Contract | Finished most of the sections, still waiting for the official time for our weekly meeting to add to the contract | Try to finish the contract as soon as the official time for weekly meeting is decided
Oct 13, 2022 |  |  |  | Yes
Oct 14, 2022 |  |  |  | Yes
Oct 15, 2022
Oct 16, 2022
Oct 17, 2022 |  |  |  | Yes
Oct 18, 2022 |  |  |  | Yes
Oct 19, 2022 |  |  |  | Yes
Oct 20, 2022
Oct 21, 2022 | Working on the brainstorming assignment | Attended weekly meeting | Attend brainstorming zoom meeting Sunday 10/23 7:30pm
Oct 22, 2022
Oct 23, 2022
Oct 24, 2022 |  |  |  | Yes
Oct 25, 2022 |  |  |  | Yes
Oct 26, 2022 |  |  |  | Yes
Oct 27, 2022 | Finish Risk slide for the Project Pitch | Attended Week 5 group meeting | Finalize the Risk slide before Saturday 10/29
Oct 28, 2022 |  |  |  | Yes
Oct 29, 2022
Oct 30, 2022
Oct 31, 2022 |  |  |  | Yes
Nov 01, 2022 |  |  |  | Yes
Nov 02, 2022 |  |  |  | Yes
Nov 03, 2022 | working with subteam on page | N/A | Start working on the assigned page with the subteam before next group meeting
Nov 04, 2022
Nov 05, 2022
Nov 06, 2022
Nov 07, 2022 | Working on the Editor Page html file | Created a draft html for the editor page | Update the Image section, add meal type section and update save button
Nov 08, 2022 | Working on the HTML file for editor page | Updated the html file, added some additional properties that were discussed on Monday meeting. Added some css styles for better visualization | Attend meeting on Thursday
Nov 09, 2022 |  |  |  | Yes
Nov 10, 2022 | Working on the editor page html | Updated some properties on the form for the editor page | Finalize the editor page html before next team meeting
Nov 11, 2022 | Working on the editor page html | Updated some properties on the form for the editor page | Finalize the editor page html before next team meeting
Nov 12, 2022
Nov 13, 2022
Nov 14, 2022 | editor page | Attended Monday meeting | Update input format for "Estimated time" on the form
Nov 15, 2022 |  |  |  | Yes
Nov 16, 2022
Nov 17, 2022 |  |  |  | Yes
Nov 18, 2022
Nov 19, 2022
Nov 20, 2022
Nov 21, 2022 | working on editor page | Uploaded meeting note Nov 21 | Error checking through W3 validator for the html editor page
Nov 22, 2022 |  |  |  | Yes
Nov 23, 2022
Nov 24, 2022 |  |  |  | Yes
Nov 25, 2022
Nov 26, 2022
Nov 27, 2022
Nov 28, 2022
Nov 29, 2022 |  |  |  | Yes
Nov 30, 2022
Dec 01, 2022 | finalize the editor page | attended Thursday group meeting, made some progress on the task populating the recipe form when editing | Add comments and documentation
Dec 02, 2022 |  |  |  | Yes
Dec 03, 2022
Dec 04, 2022
Dec 05, 2022 | send 30s video for the group video for Triston | attended 1-on-1 interview with Navya | send 30s video for the group video for Triston
Dec 06, 2022 | send 30s video for the group video for Triston before Thursday Dec 8 | attended today group meeting, made some updates on buttons design for editor page | send 30s video for the group video to Triston before Thurdays Dec 8
Dec 07, 2022

## jil269@ucsd.edu
Followup name | Group Project
User name | Kinson Liang
Date | What is your current task? | What progress you have done so far? | What future plan do you have for the task? | On Holiday
Oct 11, 2022 | Provide my introduction | Not yet | Try to finish it before Thursday
Oct 12, 2022 |  |  |  | Yes
Oct 13, 2022 | Providing my GitHub page links and writing a personal statement | All done | Ready to get the next task
Oct 14, 2022 |  |  |  | Yes
Oct 15, 2022
Oct 16, 2022
Oct 17, 2022 |  |  |  | Yes
Oct 18, 2022 | Think of the brainstorm assignment | Get some ideas | Not yet
Oct 19, 2022 | Think of the brainstorm assignment | Get some ideas | Not yet
Oct 20, 2022 |  |  |  | Yes
Oct 21, 2022 |  |  |  | Yes
Oct 22, 2022
Oct 23, 2022
Oct 24, 2022 |  |  |  | Yes
Oct 25, 2022 |  |  |  | Yes
Oct 26, 2022 |  |  |  | Yes
Oct 27, 2022 |  |  |  | Yes
Oct 28, 2022 |  |  |  | Yes
Oct 29, 2022
Oct 30, 2022
Oct 31, 2022 | Think about how to design the website | Not finished yet | Not yet
Nov 01, 2022 |  |  |  | Yes
Nov 02, 2022 |  |  |  | Yes
Nov 03, 2022 |  |  |  | Yes
Nov 04, 2022 |  |  |  | Yes
Nov 05, 2022
Nov 06, 2022
Nov 07, 2022 |  |  |  | Yes
Nov 08, 2022 |  |  |  | Yes
Nov 09, 2022 |  |  |  | Yes
Nov 10, 2022 |  |  |  | Yes
Nov 11, 2022 |  |  |  | Yes
Nov 12, 2022
Nov 13, 2022
Nov 14, 2022 |  |  |  | Yes
Nov 15, 2022 |  |  |  | Yes
Nov 16, 2022 |  |  |  | Yes
Nov 17, 2022 |  |  |  | Yes
Nov 18, 2022 |  |  |  | Yes
Nov 19, 2022
Nov 20, 2022
Nov 21, 2022 |  |  |  | Yes
Nov 22, 2022 |  |  |  | Yes
Nov 23, 2022 | work for the recipe editor page | None | Try my best
Nov 24, 2022 | work for the recipe editor page | None | Try my best
Nov 25, 2022 | work for the recipe editor page | None | Try my best
Nov 26, 2022
Nov 27, 2022
Nov 28, 2022 | work for the recipe editor page | None | Try my best
Nov 29, 2022
Nov 30, 2022 | work for the recipe editor page | None | Try my best
Dec 01, 2022 | work for the recipe editor page | None | Try my best
Dec 02, 2022 | work for the recipe editor page | None | Try my best
Dec 03, 2022
Dec 04, 2022
Dec 05, 2022 | work for the recipe editor page | None | Try my best
Dec 06, 2022
Dec 07, 2022

## masfaw@ucsd.edu
Followup name | Group Project
User name | Meron, S
Date | What is your current task? | What progress you have done so far? | What future plan do you have for the task? | On Holiday
Oct 11, 2022
Oct 12, 2022
Oct 13, 2022
Oct 14, 2022
Oct 15, 2022
Oct 16, 2022
Oct 17, 2022
Oct 18, 2022
Oct 19, 2022
Oct 20, 2022
Oct 21, 2022 | Management meeting, planning and reviewing on changes and future plans | Daily stand up fixed and up and running now Repo update Discussed logistics Planned another team meeting for Sunday 23, 2022 @7:30pm Planned weekly management meeting | Brainstorm ideas Go over specifics Assign tasks Take feedback on leadership Take feedback on TA
Oct 22, 2022
Oct 23, 2022
Oct 24, 2022 | Preparing for project pitch Preparing for team meeting Preparing for Management meeting | Brainstorm idea decided Project property designed | Team meeting in person Management meeting virtual Pitching project idea to the TA
Oct 25, 2022 | Preparing for project pitch Preparing for team meeting Preparing for Management meeting | Brainstorm idea decided Project property designed | Team meeting in person Management meeting virtual Pitching project idea to the TA
Oct 26, 2022 | Working on slides for tomorrow meeting | Brainstorm some ideas | Co-lead tomorrow’s meeting with Triston
Oct 27, 2022 | Prepare management meeting | Lead meeting of pitch slides | Finalize project pitch
Oct 28, 2022 | Attend management meeting | Lead meeting of pitch slides Updated pith program | Finalize project pitch
Oct 29, 2022
Oct 30, 2022
Oct 31, 2022 | Hosting pitch meeting | Scheduled meeting and invited participants | Start on assigning project work
Nov 01, 2022 | Coordinating workflow with Triston | Host pitch meeting and pitched some ideas | Assigning tasks to start on final project
Nov 02, 2022 | Preparing for tomorrow meeting | Reviewed git commits | Lead tomorrow meeting
Nov 03, 2022
Nov 04, 2022 | Preparing for tomorrow meeting | Reviewed git commits | Lead tomorrow meeting
Nov 05, 2022
Nov 06, 2022
Nov 07, 2022 |  |  |  | Yes
Nov 08, 2022 |  |  |  | Yes
Nov 09, 2022 |  |  |  | Yes
Nov 10, 2022 | Build css for recipes editor | Attend meeting and update main | Work on css file
Nov 11, 2022 | Set up pipe line | Meeting | Meeting
Nov 12, 2022
Nov 13, 2022
Nov 14, 2022 | Helping manage DevOps | W3 validation included in test pipeline | Prepare team meeting
Nov 15, 2022 |  |  |  | Yes
Nov 16, 2022 | Helping manage DevOps | W3 validation included in test pipeline | Prepare team meeting
Nov 17, 2022 | Helping manage DevOps | Decided on Monday meeting | Prepare team meeting
Nov 18, 2022 |  |  |  | Yes
Nov 19, 2022
Nov 20, 2022
Nov 21, 2022 | Video demo for recipe pages | Recorded a demo | Discuss on local_storage with the team
Nov 22, 2022 | Video demo for recipe pages | Recorded a demo | Discuss on local_storage with the team
Nov 23, 2022 |  |  |  | Yes
Nov 24, 2022 |  |  |  | Yes
Nov 25, 2022 |  |  |  | Yes
Nov 26, 2022
Nov 27, 2022
Nov 28, 2022 | Manage the repo commits | Project video updates | Manage the repo and add tasks
Nov 29, 2022 |  |  |  | Yes
Nov 30, 2022 |  |  |  | Yes
Dec 01, 2022 | Attend and manage repository | Attended meetings | Meet on Sunday for final video
Dec 02, 2022 |  |  |  | Yes
Dec 03, 2022
Dec 04, 2022
Dec 05, 2022 | Finishing the Project | Finished interview | Attend final meeting for project final
Dec 06, 2022 | Creating Final Video | Interviews | Finishing up
Dec 07, 2022

## rricafor@ucsd.edu
Followup name | Group Project
User name | Rappel (they/them)
Date | What is your current task? | What progress you have done so far? | What future plan do you have for the task? | On Holiday
Oct 11, 2022 | Work on group branding with Miko. | None yet | Work with Miko on brainstorming branding ideas for our group and publish on the team page.
Oct 12, 2022 | Branding with Miko | Researched ideas about branding | Work with Miko at 2pm to finish branding.
Oct 13, 2022 | Record and email intro video to team leader | Finished first in-person meeting and signed rules contract | Brainstorm ideas for website project
Oct 14, 2022 | Send intro video to Triston for group video. | I’ve finished recording my video. | I will email the video to Triston tonight.
Oct 15, 2022
Oct 16, 2022
Oct 17, 2022 |  |  |  | Yes
Oct 18, 2022 | Brainstorming Activity | Thought of ideas for group project | Attend team meeting on Thursday to discuss
Oct 19, 2022 | Brainstorming Activity | Thought of ideas for group project | Attend team meeting on Thursday to discuss
Oct 20, 2022 | Brainstorming Activity | Thought of ideas for group project | Attend team meeting on Thursday to discuss
Oct 21, 2022 | Work on brainstorming assignment | Attended Thursday meeting over zoom | Attend meeting on Sunday at 7:30pm
Oct 22, 2022
Oct 23, 2022
Oct 24, 2022 | Think of design ideas | Attended zoom meeting yesterday | Attend meeting in person on Thursday
Oct 25, 2022 |  |  |  | Yes
Oct 26, 2022 |  |  |  | Yes
Oct 27, 2022 | Finalize slides for project pitch | Added things for project timeline | Await project approval from Allison
Oct 28, 2022 |  |  |  | Yes
Oct 29, 2022
Oct 30, 2022
Oct 31, 2022 | Start working on assigned HTML pages with other developers | Attended project pitch meeting | Have assigned HTML page close to done by Thursday’s meeting
Nov 01, 2022 |  |  |  | Yes
Nov 02, 2022 | Start working on assigned HTML pages with other developers | N/A | Attend meeting tomorrow
Nov 03, 2022 | HTML for recipe view page | None | Collaborate with team on assigned HTML page
Nov 04, 2022 | HTML for recipe view page | N/A | Collaborate with team on assigned HTML page
Nov 05, 2022
Nov 06, 2022
Nov 07, 2022 | Finalize view page design | Attended meeting today | Start working on CSS
Nov 08, 2022 | Work on CSS | None | Attend meeting on Thursday
Nov 09, 2022
Nov 10, 2022 | Finish view page html/start on css | Attended meeting | Work on css over weekend
Nov 11, 2022
Nov 12, 2022
Nov 13, 2022
Nov 14, 2022 | JS for view page | Attend Monday meeting | Work on JS and testing code
Nov 15, 2022
Nov 16, 2022 |  |  |  | Yes
Nov 17, 2022 | CSS and JS for view page | Attended Thursday meeting | Meet with teammates on Saturday to work on view page
Nov 18, 2022
Nov 19, 2022
Nov 20, 2022
Nov 21, 2022
Nov 22, 2022 |  |  |  | Yes
Nov 23, 2022
Nov 24, 2022
Nov 25, 2022
Nov 26, 2022
Nov 27, 2022
Nov 28, 2022 | Work on styling | Attend sprint meeting | Make progress on main.css by Thursday
Nov 29, 2022 | Work on styling | Attend sprint meeting | Make progress on main.css by Thursday
Nov 30, 2022
Dec 01, 2022
Dec 02, 2022
Dec 03, 2022
Dec 04, 2022
Dec 05, 2022 | Finalize css | Attend meeting | Meet with team tomorrow
Dec 06, 2022
Dec 07, 2022

## jhle@ucsd.edu
Followup name | Group Project
User name | Julia Le
Date | What is your current task? | What progress you have done so far? | What future plan do you have for the task? | On Holiday
Oct 11, 2022 |  |  |  | Yes
Oct 12, 2022 | None assigned so far. | Sent the personal statement to Justin. | N/A
Oct 13, 2022 | send video to Triston | Group Bonding, Sign and upload contract | take video
Oct 14, 2022 | send video to Triston | N/A | take video
Oct 15, 2022
Oct 16, 2022
Oct 17, 2022 |  |  |  | Yes
Oct 18, 2022 |  |  |  | Yes
Oct 19, 2022 |  |  |  | Yes
Oct 20, 2022 |  |  |  | Yes
Oct 21, 2022 |  |  |  | Yes
Oct 22, 2022
Oct 23, 2022
Oct 24, 2022 |  |  |  | Yes
Oct 25, 2022 |  |  |  | Yes
Oct 26, 2022 |  |  |  | Yes
Oct 27, 2022 |  |  |  | Yes
Oct 28, 2022 |  |  |  | Yes
Oct 29, 2022
Oct 30, 2022
Oct 31, 2022 |  |  |  | Yes
Nov 01, 2022 |  |  |  | Yes
Nov 02, 2022 |  |  |  | Yes
Nov 03, 2022 | Communicate with sub team and plan | None | Contact subgroup
Nov 04, 2022 |  |  |  | Yes
Nov 05, 2022
Nov 06, 2022
Nov 07, 2022 |  |  |  | Yes
Nov 08, 2022 |  |  |  | Yes
Nov 09, 2022 |  |  |  | Yes
Nov 10, 2022 | Start Working on js file for View page | Wrote out some functions | Continue working on js file
Nov 11, 2022 |  |  |  | Yes
Nov 12, 2022
Nov 13, 2022
Nov 14, 2022 |  |  |  | Yes
Nov 15, 2022 |  |  |  | Yes
Nov 16, 2022 |  |  |  | Yes
Nov 17, 2022 | Work on Recipe view js and html | commented pseudo code for js | name elements in html for easier query
Nov 18, 2022 |  |  |  | Yes
Nov 19, 2022
Nov 20, 2022
Nov 21, 2022 |  |  |  | Yes
Nov 22, 2022 |  |  |  | Yes
Nov 23, 2022 |  |  |  | Yes
Nov 24, 2022 |  |  |  | Yes
Nov 25, 2022 |  |  |  | Yes
Nov 26, 2022
Nov 27, 2022
Nov 28, 2022 |  |  |  | Yes
Nov 29, 2022 |  |  |  | Yes
Nov 30, 2022 |  |  |  | Yes
Dec 01, 2022 | Work on css and view page | List out fixes that need to be addressed | Talk with my view page members so address concerns before Sunday
Dec 02, 2022 | Work on css and view page | List out fixes that need to be addressed | Talk with my view page members so address concerns before Sunday
Dec 03, 2022
Dec 04, 2022
Dec 05, 2022 | one-on-one interview | n/a | n/a
Dec 06, 2022
Dec 07, 2022

## m9brown@ucsd.edu
Followup name | Group Project
User name | Miko Brown
Date | What is your current task? | What progress you have done so far? | What future plan do you have for the task? | On Holiday
Oct 11, 2022 |  |  |  | Yes
Oct 12, 2022 |  |  |  | Yes
Oct 13, 2022 | Branding | Completed branding | Nothing, it is completed.
Oct 14, 2022 |  |  |  | Yes
Oct 15, 2022
Oct 16, 2022
Oct 17, 2022 |  |  |  | Yes
Oct 18, 2022 |  |  |  | Yes
Oct 19, 2022 |  |  |  | Yes
Oct 20, 2022 |  |  |  | Yes
Oct 21, 2022 |  |  |  | Yes
Oct 22, 2022
Oct 23, 2022
Oct 24, 2022 |  |  |  | Yes
Oct 25, 2022 |  |  |  | Yes
Oct 26, 2022 |  |  |  | Yes
Oct 27, 2022 | Finishing scope slide for project pitch | Started outline of slide | Finalize slide contents by sunday night
Oct 28, 2022 |  |  |  | Yes
Oct 29, 2022
Oct 30, 2022
Oct 31, 2022 | Meeting | Presented | Completed
Nov 01, 2022 |  |  |  | Yes
Nov 02, 2022 |  |  |  | Yes
Nov 03, 2022 | Team meeting | Completed meeting, picked teams | Done
Nov 04, 2022 |  |  |  | Yes
Nov 05, 2022
Nov 06, 2022
Nov 07, 2022 | Homepage | Finished starting plan | Finalize page design
Nov 08, 2022 |  |  |  | Yes
Nov 09, 2022 |  |  |  | Yes
Nov 10, 2022 | Homepage | Meeting deciding recipe architecture | Implement html
Nov 11, 2022 |  |  |  | Yes
Nov 12, 2022
Nov 13, 2022
Nov 14, 2022 |  |  |  | Yes
Nov 15, 2022 |  |  |  | Yes
Nov 16, 2022 |  |  |  | Yes
Nov 17, 2022 | Homepage prototype | Created initial outline | Finish prototype
Nov 18, 2022 |  |  |  | Yes
Nov 19, 2022
Nov 20, 2022
Nov 21, 2022 |  |  |  | Yes
Nov 22, 2022 |  |  |  | Yes
Nov 23, 2022 |  |  |  | Yes
Nov 24, 2022 |  |  |  | Yes
Nov 25, 2022 |  |  |  | Yes
Nov 26, 2022
Nov 27, 2022
Nov 28, 2022 | 11/28 Meeting | Completed meeting | Meet thursday 12/1
Nov 29, 2022 |  |  |  | Yes
Nov 30, 2022 |  |  |  | Yes
Dec 01, 2022 |  |  |  | Yes
Dec 02, 2022 |  |  |  | Yes
Dec 03, 2022
Dec 04, 2022
Dec 05, 2022 |  |  |  | Yes
Dec 06, 2022 |  |  |  | Yes
Dec 07, 2022

## aturner@ucsd.edu
Followup name | Group Project
User name | Allison Turner (TA)
Date | What is your current task? | What progress you have done so far? | What future plan do you have for the task? | On Holiday
Oct 11, 2022
Oct 12, 2022
Oct 13, 2022
Oct 14, 2022
Oct 15, 2022
Oct 16, 2022
Oct 17, 2022
Oct 18, 2022
Oct 19, 2022
Oct 20, 2022
Oct 21, 2022
Oct 22, 2022
Oct 23, 2022
Oct 24, 2022
Oct 25, 2022
Oct 26, 2022
Oct 27, 2022
Oct 28, 2022
Oct 29, 2022
Oct 30, 2022
Oct 31, 2022
Nov 01, 2022
Nov 02, 2022
Nov 03, 2022
Nov 04, 2022
Nov 05, 2022
Nov 06, 2022
Nov 07, 2022
Nov 08, 2022
Nov 09, 2022
Nov 10, 2022
Nov 11, 2022
Nov 12, 2022
Nov 13, 2022
Nov 14, 2022
Nov 15, 2022
Nov 16, 2022
Nov 17, 2022
Nov 18, 2022
Nov 19, 2022
Nov 20, 2022
Nov 21, 2022
Nov 22, 2022
Nov 23, 2022
Nov 24, 2022
Nov 25, 2022
Nov 26, 2022
Nov 27, 2022
Nov 28, 2022
Nov 29, 2022
Nov 30, 2022
Dec 01, 2022
Dec 02, 2022
Dec 03, 2022
Dec 04, 2022
Dec 05, 2022
Dec 06, 2022
Dec 07, 2022

## aschade@ucsd.edu
Followup name | Group Project
User name | Andy Schade
Date | What is your current task? | What progress you have done so far? | What future plan do you have for the task? | On Holiday
Oct 11, 2022 | My current task is to work on the team website with Justin. | No progress. | I hope we are able to make a good looking team summary and website.
Oct 12, 2022 | I am writing a Bio for our group web page. | Wrote a few sentences. | I hope that all the bios come together nicely and look clean on the team website.
Oct 13, 2022 | Finishing the Team Page and Team meeting | We just finished both of those today with our group. | None because we just finished.
Oct 14, 2022 |  |  |  | Yes
Oct 15, 2022
Oct 16, 2022
Oct 17, 2022 |  |  |  | Yes
Oct 18, 2022 |  |  |  | Yes
Oct 19, 2022 |  |  |  | Yes
Oct 20, 2022 | Catching up with my group on the meeting today | opened the meeting notes. | to find out my tasks for the week and get to completing them.
Oct 21, 2022 |  |  |  | Yes
Oct 22, 2022
Oct 23, 2022
Oct 24, 2022 |  |  |  | Yes
Oct 25, 2022 |  |  |  | Yes
Oct 26, 2022 |  |  |  | Yes
Oct 27, 2022 |  |  |  | Yes
Oct 28, 2022 |  |  |  | Yes
Oct 29, 2022
Oct 30, 2022
Oct 31, 2022 |  |  |  | Yes
Nov 01, 2022 |  |  |  | Yes
Nov 02, 2022 |  |  |  | Yes
Nov 03, 2022 |  |  |  | Yes
Nov 04, 2022 |  |  |  | Yes
Nov 05, 2022
Nov 06, 2022
Nov 07, 2022 |  |  |  | Yes
Nov 08, 2022 |  |  |  | Yes
Nov 09, 2022 |  |  |  | Yes
Nov 10, 2022 | Working on getting caught up on material. | Good amount of work. | To do more catch up.
Nov 11, 2022 | Working on getting caught up on material. | Good amount of work. | To do more catch up.
Nov 12, 2022
Nov 13, 2022
Nov 14, 2022 | Working on getting caught up on material. | Good amount of work. | To do more catch up.
Nov 15, 2022 |  |  |  | Yes
Nov 16, 2022 |  |  |  | Yes
Nov 17, 2022 | Making the meeting Notes for my group. | I am currently writing them | I am planning to commit these meeting notes
Nov 18, 2022 | Team meeting tonight | Scheduled the meeting | My plan is to have a productive meeting with my team
Nov 19, 2022
Nov 20, 2022
Nov 21, 2022
Nov 22, 2022
Nov 23, 2022
Nov 24, 2022
Nov 25, 2022
Nov 26, 2022
Nov 27, 2022
Nov 28, 2022
Nov 29, 2022
Nov 30, 2022
Dec 01, 2022
Dec 02, 2022
Dec 03, 2022
Dec 04, 2022
Dec 05, 2022
Dec 06, 2022
Dec 07, 2022

## jjl025@ucsd.edu
Followup name | Group Project
User name | Justin Lau
Date | What is your current task? | What progress you have done so far? | What future plan do you have for the task? | On Holiday
Oct 11, 2022 | webpage | get personal descriptions | complete tomorrow
Oct 12, 2022 |  |  |  | Yes
Oct 13, 2022 | webpage | completed | publish page
Oct 14, 2022 |  |  |  | Yes
Oct 15, 2022
Oct 16, 2022
Oct 17, 2022 |  |  |  | Yes
Oct 18, 2022 |  |  |  | Yes
Oct 19, 2022 |  |  |  | Yes
Oct 20, 2022 |  |  |  | Yes
Oct 21, 2022 |  |  |  | Yes
Oct 22, 2022
Oct 23, 2022
Oct 24, 2022 |  |  |  | Yes
Oct 25, 2022 |  |  |  | Yes
Oct 26, 2022 |  |  |  | Yes
Oct 27, 2022 | meeting notes | complete | n/a
Oct 28, 2022 |  |  |  | Yes
Oct 29, 2022
Oct 30, 2022
Oct 31, 2022 |  |  |  | Yes
Nov 01, 2022 |  |  |  | Yes
Nov 02, 2022 |  |  |  | Yes
Nov 03, 2022 |  |  |  | Yes
Nov 04, 2022 |  |  |  | Yes
Nov 05, 2022
Nov 06, 2022
Nov 07, 2022 |  |  |  | Yes
Nov 08, 2022 |  |  |  | Yes
Nov 09, 2022 |  |  |  | Yes
Nov 10, 2022 |  |  |  | Yes
Nov 11, 2022 | View page | Added comments, show recipe object | edit some code
Nov 12, 2022
Nov 13, 2022
Nov 14, 2022 | View page | edited some code | Add more code
Nov 15, 2022 |  |  |  | Yes
Nov 16, 2022 |  |  |  | Yes
Nov 17, 2022 |  |  |  | Yes
Nov 18, 2022 |  |  |  | Yes
Nov 19, 2022
Nov 20, 2022
Nov 21, 2022 | finished implementing functionality for view page | finished view page functionality | working on styling and organization
Nov 22, 2022 |  |  |  | Yes
Nov 23, 2022 |  |  |  | Yes
Nov 24, 2022 |  |  |  | Yes
Nov 25, 2022 |  |  |  | Yes
Nov 26, 2022
Nov 27, 2022
Nov 28, 2022 |  |  |  | Yes
Nov 29, 2022 |  |  |  | Yes
Nov 30, 2022 |  |  |  | Yes
Dec 01, 2022 |  |  |  | Yes
Dec 02, 2022 | implement fixes to view page | completed | help with css and testing
Dec 03, 2022
Dec 04, 2022
Dec 05, 2022
Dec 06, 2022
Dec 07, 2022